# Final Indicator Description: Catch Per Unit Effort (CPUE):

# Raizes Azuis Project

16.6.2026

# INDICATOR 01, Fisheries CPUE, Parameters

- Catch Per Unit Effort (CPUE) of key fisheries species in project-supported community fishing areas.  This is the main parameter that will be collected.

- Rapid size-structure monitoring (RSSM): 7 shortest + 7 longest individuals per principal species visible in the landed catch. These measurements will be used as a rapid indicator of landed size range and changes in size structure over time. The method is not intended to estimate full length-frequency distributions or mean catch length.

The Ocean Guardians monitoring system has two linked but separate components:

- Catch/effort monitoring: weight-based CPUE. Measures fisheries recovery using total biomass of catch.

- Rapid size-structure monitoring: 7 shortest + 7 longest individuals per principal species.  Alerts managers to any changes in the population structure of monitored species over time (especially loss of large fish or increasing dominance of very small fish).

## Indicator Type

- Catch Per Unit Effort (CPUE) Impact Indicator (Livelihoods / Fisheries Recovery)

- Rapid size-structure monitoring (RSSM):   This is not used to calculate CPUE. It is used to alert managers to changes in landed size structure over time, especially loss of large fish or increasing dominance of very small fish, both of which might mean overfishing.

## Definition

Catch Per Unit Effort (CPUE) measures the quantity of fish caught per standardized unit of fishing effort (day). It serves as a proxy for fish abundance and fisheries recovery over time within community-managed fishing areas supported by the Raízes Azuis Project.

CPUE is calculated as total catch (kg) divided by standardized fishing effort (fisher-days), using consistent methods across all monitoring periods.

Rapid Size-Structure Monitoring: 7 shortest + 7 longest individuals per principal species.  Gives an average size structure that can be useful for fisheries management.  This gives:

- minimum observed landed size

- maximum observed landed size

- mean of the smallest group

- mean of the largest group

- spread/range between small and large fish

- trend over time in whether the smallest fish are getting smaller/larger

- trend over time in whether large fish are disappearing or returning

All of these are useful for monitoring size structure pressure, especially when the alternative is bad data or no data.  The main limitation is that it over-samples the extremes by design. So you cannot say “the average fish length was X” or “X% of fish were below maturity size” unless you also have a representative sample. FAO guidance is clear that length samples should be random if they are meant to represent the whole catch and avoid bias.   Fishkit guidance also explicitly recognizes that ideal fishery-dependent length sampling often has to be adapted to capacity-limited, data-limited fisheries.

## Unit of Measurement

CPUE:  Kilograms per unit effort (kg per fisher-hour)

This means that a boat with 6 fishers, fishing for 1 hour, is 6 fisher-hours.

RSSM:    total and average cms/ 7 smallest fish/species/day

-and-        total and average cms/ 7 biggest fish/species/day

A note about sample sizes:   Daily RSSM measurements will be pooled by species and week to produce weekly average values for the smallest-size group and largest-size group. Where five monitoring days are completed, the weekly sample may include up to 35 fish in each size group per species. These data are intended to support trend detection in landed size range, not estimation of true population length-frequency.

## Disaggregation

- By community / landing site

- By gear type (e.g., net, line, trap)

- By key species (target species defined by project)

- By season (optional, if relevant)

## Method of Calculation

CPUE:

CPUE=Total catch (kg)Total fisher-hours

Where:

- Total catch = sum of recorded fish catch per sampling period

- Effort = standardized measure (e.g., number of fishers × hours fished)

RSSM:

RSSM shortest =total length of fish measured(cm)number fish measured

RSSM longest =total length of fish measured(cm)number fish measured

NB:  For very small catches, if ≤14 fish of a species are landed, measure all individuals, and put half in the longest group and half in the shortest. If the number is uneven, put the middle fish to the “shortest” group. CPUE remains calculated only from weight and effort; RSSM is used only as a rapid size-structure signal.

## Data Collection Methodology

Approach:
Community-based monitoring conducted by trained Ocean Guardians using standardized catch and effort recording forms.   Forms will be filled on Smartphone with paper backup.

This will be triangulated with interviews with fishers at regular intervals, to gain qualitative information about CPUE, number of fishers/ boats, and distances and travel times to fishing grounds.

# Procedure, CPUE, Effort and Catch reporting forms:

- Define landing site responsibilities for each Ocean Guardian.

- For each day, Ocean Guardians record:

  - Fisher ID

  - Date and location

  - Gear type used

  - Duration of fishing activity (hours)

  - Total catch (kg)

  - Key species composition (Total kg per species)

  - RSSM (stratified by species)

  - Record zero catch days and differentiate from days when no one goes fishing.

- Standardize effort units across all sites (fisher-hours).

- Aggregate data weekly and calculate CPUE per site and overall.

- Aggregate data weekly and calculate RSSM shortest and RSSM longest per site and overall.

Quality Control:

- Be consistent over time.

- Periodic spot checks by supervisors

- Cross-learning between Guardians for landing site observations

- All Ocean Guardians will use bump boards for length and mechanical scales for weight.

Frequency of Data Collection:

- Daily at assigned fishing landing sites

- Intertidal collectors will be encouraged to take their catch to each landing site to be collected.

- Aggregation and reporting: Monthly (but data will be discriminated on weekly basis for uploading)

- Upload to dashboard: Monthly

- Analysis: Quarterly and annually

## Baseline

Month by month comparison based on first year of data

## Target

CPUE: Percentage increase in CPUE over baseline (target to be defined based on baseline results and ecological context). Although increases in CPUE have manifested themselves quite quickly in other areas of Mozambique, the Raizes Azuis Project must adopt a more cautious approach, due to the time needed to establish community management areas and no- take zones.  Over the life of the project, CPUE may not rise; however this rise will certainly be felt over a 5-year time horizon.  The estimate of 7% over five years seems to be reasonable, based on research internationally.

RSSM:  Is more complicated to interpret, yet still valuable.  Over several years, managers would generally expect:

- The average length of the 7 largest fish to remain stable or increase.

- The average length of the 7 smallest fish to remain stable and above juvenile sizes.

- The gap between smallest and largest fish to remain relatively consistent.

- Regular occurrence of large, mature individuals in catches.

## Data Source

- Ocean Guardian catch monitoring forms (ZOHO Creator or paper-based tools)

- Landing site verification records (sample-based by supervisor)

## Responsible Party

- Primary: Ocean Guardians (community monitors)

- Oversight: Project MEL Team/ Coalition Team member (each team indicates their responsible supervisor)

## Verification Method

- Random spot checks at landing sites/ Comparison with sampled landing data

- Periodic data audits and validation by project staff

## Key Assumptions

- Fishing effort can be consistently standardized across monitoring periods

- Sampled fishers represent broader fishing patterns

- No major external shocks (e.g., extreme weather, market collapse) significantly distort fishing effort or reporting (Thematic analysis to capture qualitative data:  Annually)

## Limitations

- CPUE may be influenced by changes in fishing behavior or gear efficiency

- Requires consistent participation of fishers over time

# PREPARATORY WORK FOR INDICATOR 01 (CPUE MONITORING plus RSSM)

## DEFINE THE MONITORING DESIGN (FOUNDATIONAL)

### Select Monitoring Sites

- Identify target landing sites and assign Ocean Guardian(s) to each

- Confirm:

  - Active fishing activity

  - Accessibility

  - Safety

- Establish definitive list (no changes later unless justified)

### Define Target Fisheries

- Identify:

  - Key species (e.g., prawns, crabs, clams, fish species, etc.) and apply standard names/codes Vernacular, Portuguese, scientific, etc.) be consistent across sites

  - Priority gears (nets, lines, traps, hand collection, etc)

### 👉 Output:

- Site definition

- Standard species list (coded/ named)

- Gear classification system (include hand capture for mollusk/ intertidal collection)

### 👉 Output:

Written definitions:

“Effort = number of fishers × hours fished”

“ Catch per unit effort = kg fish captured / (number of fishers × hours fished)

Calculate catch per unit effort overall and for indicator species (to be selected, but it is recommended to use at least calculate for crabs, shellfish, and important fish species- Raizes Azuis partners will define).

## Select Field methodology

It is recommended to choose the methodology described in the attached document “Fisheries Field Methodology Ocean Guardians 22.4.2026.”  Two changes will be needed.

- Add another capture method (question no. 3) which will be hand capture.

- Unless by special request from a partner or the GoM, Ocean guardians will not be taking tissue samples (no. 9).

It is recommended to use the recording sheet entitled “FICHA DE AMOSTRAGEM Raizes Azuis 5.6.2026.”

Thanks to Raizes Azuis partners for providing these examples.

### What to do if there are many fishers and boats at the landing site and you cannot measure all the catch in the time available

Where all boats cannot be measured, Ocean Guardians shall sample boats consecutively in order of arrival during the established monitoring window. The Guardian shall not choose boats based on catch size, fisher identity, gear type, or willingness, except where a fisher refuses participation or leaves before being measured. The number of boats sampled, number of refusals, start time, and end time shall be recorded. This approach is intended to provide a consistent annual index of catch and effort, rather than a full census of all landings.

This is defensible for Raizes Azuis because the objective is trend monitoring, not formal stock assessment.

Output:

- Written protocol

## SELECT AND FORMALIZE OCEAN GUARDIANS

### Selection Criteria

- Respected in community

- Literate (preferred but not mandatory)

- Active in fisheries or trusted observers

- Gender inclusion (strongly recommended)

### Recruitment

- Formal community validation

- Transparent selection process

### Contracts / Agreements

- Define:

  - Roles

  - Time commitment

  - Payment / incentives

  - Code of conduct

### Assignment

- Assign guardians to:

  - Specific sites

## BUILD DATA COLLECTION TOOLS

### Build Tools

Choose:

- ZOHO Creator

- Paper backup forms (mandatory)

### Create Coding Systems

- Species codes

- Gear codes

- Site codes

- Enumerator IDs

### Build Validation Rules

- No negative values

- Mandatory fields

## ESTABLISH MEASUREMENT STANDARDS (CRITICAL FOR DATA QUALITY)

### Catch Measurement

- Provide Standard Toolkit:

  - Mechanical scales

  - Standardized buckets (for bulk weighing of small fish)

  - Meter sticks, tapes measures, or bump boards

  - Tarpaulin

  - Water bottle

  - Pens, waterproof plastic folders, and forms to fill in.

  - Simple illustrated guide to catch species

  - Smartphone and charger (NB: already standardized).

### Time Measurement

  - Record the time of the sampling for each boat sampled

  - Effort is to be measured in ‘hours fished’

  - Record and discriminate ‘days fished with no fish’ and ‘days not fished’; days not fished do not enter into our calculations but the hours fished on days with no fish do.

  - NB:  In project area, fishing is generally not done on Sundays.  These are to be recorded as ‘days not fished.’

### Species Identification

- Develop:

  - Simple illustrated guide

  - Grouping system (important species disaggregated individually, others collectively, caranguejo, ostra, etc.)

## TRAINING PROGRAM

### Ocean Guardian Training

Topics:

- Purpose of monitoring

- How to record data

- Use of tools (ODK/paper)

- Species identification

- Ethics and neutrality

### Practical Field Training

- Simulated data collection

- Real landing site practice

- Supervised first entries

### Community Orientation

- Explain:

  - Why data is collected

  - What will NOT happen (no enforcement misuse)

  - Benefits to community

## PILOT TESTING (CRITICAL — DO NOT SKIP)

### Pilot Duration

- 2–4 weeks minimum

### Systems Test:

- Data forms

- Guardian performance

- Fisher cooperation

- Data variability

### Identify Problems

- Missing data

- Misinterpretation

- Over-reporting / under-reporting

- Others?

### Tweak Tools and Protocols

- Adjust BEFORE full rollout

## DATA MANAGEMENT SYSTEM SETUP

### Dashboard Design

- Centralized dataset (MUVA server and website)

- Design of dashboard is with MUVA MEL team

### Data Flow Definition and responsibilities

- Define: who collects → who submits → who validates → who analyzes

### Data Cleaning Protocol

- Weekly checks

- Error flags

- Follow-up corrections

### Backup System

- Offline + cloud backup

## QUALITY CONTROL SYSTEM

### Spot Checks

- Random visits to landing sites

- Compare reported vs observed

### Supervisor Reviews

- Weekly review of submissions

### Cross-Validation

- Compare:

  - Sentinel data vs supervisor’s landing observations

## BASELINE ESTABLISHMENT

### Initial Data Collection Period

- Maintain monthly comparisons with first year data (fishing results vary throughout the yearly cycle)

### Baseline Calculation

- Average CPUE per site per month

- Per gear

- Per species/ classe

### Documentation

- Baseline report

- Methodology clearly documented

## COMMUNITY VALIDATION & BUY-IN

### Community Meetings (each coalition member)

- Present:

  - Monitoring approach

  - Expected benefits

### Feedback Integration

- Adjust if necessary

### Transparency Mechanism

- Share results periodically throughout the coalition

## RISK MITIGATION PREPARATION

- Identify and plan for:

- Fisher mistrust

- Scarce or shortage of information

- Guardian dropout (train 2 times the number of people at initial training)

- Seasonal variability (is expected, that’s why we compare month to month across the year)

- Extreme weather events (Thematic analysis to be able to tell the qualitative stories)

## CRITICAL SUCCESS FACTORS (FROM EXPERIENCE & LITERATURE)

If we only get 4 things right, the system will work:

- Effort is standardized correctly

- Fishers are monitored consistently

- Guardians are trained and supervised

- Pilot phase is taken seriously

## FINAL OUTPUT OF PREPARATION PHASE

Before starting full monitoring, you must have:

✔ Written protocol (field manual- see draft from Peter)
✔ Trained Ocean Guardians
✔ Working data collection tools
✔ Tested system (pilot completed)
✔ Defined baseline methodology

# Qualitative data collection for triangulation of CPUE data

## Purpose

Quantitative CPUE monitoring provides an important proxy for fisheries productivity and ecosystem recovery. However, CPUE data alone cannot fully explain:

- changes in fisher behavior,

- shifts in fishing pressure,

- changing travel patterns,

- fisher perceptions of resource abundance,

- or broader socio-economic dynamics affecting fisheries.

For this reason, the Raízes Azuis Project will implement an annual qualitative data collection process with fishers to triangulate and contextualize CPUE findings.

This qualitative component will:

- help interpret changes observed in CPUE data,

- identify trends not immediately visible through quantitative monitoring,

- capture fisher knowledge and perceptions,

- and support thematic analysis of fisheries change over time.

The system is not intended to replace CPUE monitoring, but rather to strengthen interpretation and adaptive management.

## QUALITATIVE TRIANGULATION METHODOLOGY

### Frequency

Qualitative fisher interviews will be conducted:

- Annually

- During one predetermined monitoring week each year

- Ideally during the same seasonal period each year for comparability

## Sampling Approach

During the designated monitoring week:

- Each Ocean Guardian will attempt to interview every fisher encountered at their assigned landing site.

- Interviews should include:

  - different gear users,

  - different age groups,

  - women harvesters and processors where relevant,

  - intertidal collectors,

  - boat and non-boat fishers.

This approach is intended to maximize representativeness within the constraints of community-based monitoring.

### Interview Duration

Maximum interview duration:

- 15 minutes

Interviews must remain:

- concise,

- respectful,

- and minimally disruptive to fishing activities.

## Enumerator Guidance

Ocean Guardians must:

- read questions exactly as written,

- avoid leading respondents,

- remain neutral,

- avoid suggesting “correct” answers,

- and record responses faithfully.

Where respondents elaborate beyond the structured responses:

- important comments should be summarized in the notes section.

## Data Collection Method

Interviews will be conducted:

- verbally,

- individually,

- at landing sites or immediately adjacent areas.

Data collection tools:

- Smartphone form with paper backups

## QUALITATIVE TRIANGULATION QUESTIONNAIRE

### Section A. Respondent Information

- Landing Site

- Date

- Ocean Guardian ID

- Respondent Gender

- Estimated Age Category

  - Under 25

  - 25–40

  - 41–60

  - Over 60

- Main Fishing Method / Gear Used

- Years Fishing in This Area

### Section B. Perceptions of Fish Availability and Catch

#### Q1. Compared to 5 years ago, how would you describe the amount of fish you catch?

- Much less

- Less

- About the same

- More

- Much more

#### Q2. Compared to 5 years ago, how would you describe the size of fish being caught?

- Much smaller

- Smaller

- About the same

- Larger

- Much larger

#### Q3. Compared to previous years, how easy is it now to find fish?

- Much harder

- Harder

- About the same

- Easier

- Much easier

#### Q4. Are there species that are now difficult to find compared to before?

- Yes

- No

If yes:

- Which species? (Open-ended)

#### Q5. Are there any specific events (floods, storms, etc.) that changed the amount of fish caught?

- Yes

- No

If yes:

- Which events and what happened to the fishing? (Open-ended)

### Section C. Fishing Effort and Fishing Pressure

#### Q6. Compared to 3 years ago, are there now more or fewer fishers using this fishing area?

- Many fewer

- Fewer

- About the same

- More

- Many more

#### Q7. Compared to before, are there now more or fewer fishing boats operating in this area?

- Many fewer

- Fewer

- About the same

- More

- Many more

#### Q8. Compared to previous years, do fishers now spend more time fishing to catch the same amount of fish?

- Much less time

- Less time

- About the same

- More time

- Much more time

#### Q9. Compared to previous years, do fishers now travel further to fishing grounds?    Include an estimate of daily time schedule and distances (kms) to be travelled).

- Much shorter distances

- Shorter distances

- About the same

- Further

- Much further

#### Q10.  How much time do you spend traveling to fishing grounds, on average?   And how far do you travel?

Time:    ____________ hours travelling to fishing grounds

Distance:_____________ kms

#### Q11. Compared to before, how would you describe fuel or transport costs associated with fishing?

- Much lower

- Lower

- About the same

- Higher

- Much higher

### Section D. Perceptions of Marine Management

#### Q12. Do you think marine resources in this area are being managed better than before?

- Much worse

- Worse

- About the same

- Better

- Much better

#### Q13. Do you believe No-Take Zones or protected areas help fisheries recovery?

- Strongly disagree

- Disagree

- Neutral / unsure

- Agree

- Strongly agree

#### Q14. Do you feel community members generally respect fisheries rules?

- Strongly disagree

- Disagree

- Neutral / unsure

- Agree

- Strongly agree

#### Q15.  Why or why not?

(Open ended)

### Section E. Open-Ended Questions

#### Q16. In your opinion, what are the biggest changes happening in local fisheries?

(Open-ended)

#### Q17. What do you think are the main causes of these changes?

(Open-ended)

#### Q18. Have you changed the way you fish in recent years? Why?

(Open-ended)

#### Q19. What do you think should be done to improve fisheries in this area?

(Open-ended)

#### Q20. Is there anything else you would like to share about fisheries or marine resources in this area?

(Open-ended)

## DATA ANALYSIS

### Quantitative Analysis

Likert-scale questions will be analyzed quantitatively through:

- frequency distributions,

- average scores,

- comparison across years,

- comparison across sites,

- and trend analysis.

This will allow fisher perceptions to be compared with:

- CPUE trends,

- governance indicators,

- and ecological observations.

### Qualitative Analysis

Open-ended responses will be subjected to thematic analysis.

Themes may include:

- declining catches,

- increased fishing pressure,

- illegal fishing,

- changing species composition,

- governance concerns,

- perceptions of No-Take Zones,

- climate and weather impacts,

- or livelihood stress.

Thematic analysis will:

- identify recurring issues,

- capture emergent trends,

- and provide contextual interpretation for quantitative findings.

Illustrative quotations may be extracted for reporting purposes where appropriate.

## INTEGRATION WITH CPUE and RSSM INTERPRETATION

Qualitative findings will be used to contextualize CPUE and RSSM trends.

Examples:

- CPUE increases accompanied by reports of reduced travel distance may strengthen confidence in fisheries recovery.

- Stable CPUE combined with reports of greatly increased fishing effort may indicate hidden pressure on fisheries.

- Declining CPUE accompanied by reports of increased fisher numbers may indicate rising exploitation pressure.

The qualitative system therefore functions as:

- a triangulation mechanism,

- an interpretive tool,

- and an early warning system for fisheries change.

## RESPONSIBLE PARTIES

Primary collection:

- Ocean Guardians

Oversight and analysis:

- MEL Team

- Coalition technical staff

## OUTPUTS

Outputs from the qualitative triangulation process may include:

- annual thematic summaries,

- integration into CPUE reports,

- dashboard summaries,

- case examples,

- and adaptive management recommendations.

## CRITICAL SUCCESS FACTORS

The qualitative triangulation system will function best if:

- Interviews are conducted consistently each year

- Ocean Guardians remain neutral

- Questions are asked exactly as written

- Fishers feel safe expressing honest opinions

- Results are analyzed together with quantitative CPUE data

# Next Steps (6.5.2026):

- Discuss with Lelio and call with Coalition members to evaluate this final draft

- Do we have a illustrated guide to species or must we make one?

- Did Juliet get the standardized kit sorted out?

- How will we brief/ train Ocean Guardians?

- Irio to work on data collection tools.  Are these ready?  Is the dashboard ready?

https://www.fao.org/4/s8480e/s8480e04.HTM?utm

https://fisheriestoolkit.org/the-science-behind-fishkit/fishery-dependent-length-data/?utm

The Nature Conservancy (2022). Sea Change: Costs and Benefits of Marine Protected Areas. Editors: McGowan J., Gammage S., Escovar-Fadul X., Weis S., Hansen A., and Garvey M. Arlington, VA. (pp. 36).